## Sheet1
IMPLEMENTATION WORKSHEET |  |  | Plant (Company) |  |  | Project
|  |  | By |  |  | With
|  |  | Date |  |  | Sheet | of
WHAT |  |  |  |  | WHO | WHEN | STATUS
MAKE READY | PLAN | 1. Start planning the installation
2. Establish sequence and timing of moves
3. Inventory materials and equipment to move
4. Get disposition of non-moving material and equipment
5. Schedule moves in detail
6. Assign move numbers; check vs inventory & equipment (tag) number
7. Verify procedural changes and timing
8.
| PROVIDE | 1. Decide who will make moves
2. Secure bids as necessary
3. Determine and reserve moving equipment required
4. Set up communications for both ends of move
5. Appoint key person for each area
6. Get work order(s) for moves
7. Verify delivery for any new equipment
8.
| PREPARE | 1. Prepare new locations -- physical area, conditions, auxiliaries
2. Broadcast plans
3. Brief personnel specifically involved
4. Mark everything to move; identification, move no., destination
5. Disconnect or ready equipment
6. Check out equipment and release to movers
7. Complete required training
8.
DO | INSTALL | 1. Move equipment intact to reduce re-assembly time
2. Move close to spot to reduce line-up and hook-up time
3. Post move performance as accomplished
4. Keep moving crew informed, coordinated
5. Be on hand -- layout interpretation
6. Be on hand -- auxiliaries interpretation
7. Be on hand -- procedures interpretation
8
PUT AWAY | HOOK-UP | 1. Spot equipment; check location
2. Temporary hook-ups where needed
3. Check and release for permanent connections
4. Inspect the installation & release for tryout
5. Maintenance tryout
6. Release to operating group; secure acceptance
7.
8.
| CLEAN-UP | 1. Survey-inspect old and new areas
2. Schedule & assign clean-up -- old and new areas
3. Verify layout as installed
4. Verify auxiliary service as installed
5. Verify or adjust layout & service-specification records
6. Recap installation costs and performance
7. Final sign-off by operating group
8.
Reference Notes:
a. |  |  |  | d.
b. |  |  |  | e.
c. |  |  |  | f.